## Time
Task	Datum	Zeitaufwand in min
Read Requirement document - define requirements	02.01.2021	15
Create github repo for the setup project and commit protocoll	02.01.2021	15
Read tutorial about docker compose and setup postgress in docker-compose.yml	04.01.2021	30
Create Camunda Spring Boot app and start with dependency postgres db	04.01.2021	120
Write automation script for current setup	05.01.2021	30
Create three VMs with Docker compose / Define depends_on and add build / compose to startup script	05.01.2021	30
Read documentation / Create Postman Collection / Investigate Camunda Rest API	06.01.2021	60

## Requirements
Ticket	Name	Description	Status	Reference
JPA-01	Create protocoll		In Progress
JPA-02	Github Repo erstellen		Done	https://github.com/barblin/camunda-alanda-setup
JPA-03	Create three VMs with Docker compose		Done	https://github.com/barblin/camunda-alanda-setup
JPA-04	Create VM with Postgres DB		Done	https://github.com/barblin/camunda-alanda-setup/blob/develop/docker-compose.yml
JPA-05	Create Camunda Spring Boot app		Done	https://github.com/barblin/camunda-alanda-setup/tree/develop/com.alanda.camunda.services
JPA-06	Integration Test DB <-> Camunda Service	Use Feature "Cockpit & get / query results" to test if / Camunda Engine + Service / communicate properly with the DB.	Done
JPA-07	Feature: A customer wants to browse the get / query results via browser to see how many / successful camunda processes have been / executed	Fully implement and test feature and / create integration test to verify. / Addtional Information: / Das Service soll eine DB-Query / absetzen (z.B. Zähle alle bisher / durchlaufenen Camunda Prozesse) / & das Ergebnis inkl. Timestamp / in-memory (Liste) speichern. / Der Aufruf des REST-Endpoints (c) / soll den Inhalt des Caches als / JSON zurückliefern	Open
JPA-08	Java Spring Boot App with example rest API		Open
JPA-09	Feature: A customer wants to be able to deploy / a new process via local file to camunda	Fully implement and test feature and / create integration test to verify. / Addtional Information: / Ziel ist, dass nach Start der / Applikation in der "leeren" / Camunda-Instanz ein neuer Prozess / angelegt ist. Wenn dieser nun via / Camunda Cockpit gestartet wird, / ist nach Durchlaufen des Prozesses / durch den REST-Endpoint (c) vom / Container "Camunda-Instanz" das / Ergebnis des Service-Calls nachlesbar.	Open
JPA-10	Test with git bash		Done
JPA-11	Write setup guide		Open
JPA-12	Test on linux environment		Open